## Jira_Backlog
Issue ID | User Story | Description | Story Points | Assigned To | Branch Name | Priority | Status
SA-100 | Project Documentation | Create SRS, Jira Task Sheet, Presentation, Final Report | 4 | Pawan | document-setup | High | To Do
SA-101 | Project Setup | Initialize Flask project structure and environment setup | 3 | Pawan | feature/project-setup | High | To Do
SA-102 | Data Collection | Collect and prepare labeled sentiment dataset (CSV format) | 5 | Rahul | feature/data-collection | High | To Do
SA-103 | Text Preprocessing Module | Implement text cleaning, tokenization, stopword removal | 5 | Anjali | feature/text-preprocessing | High | To Do
SA-104 | Naive Bayes Model | Train and save Naive Bayes sentiment classification model | 8 | Pawan | feature/naive-bayes-model | High | To Do
SA-105 | LSTM Model | Build and train LSTM-based sentiment model | 13 | Rahul | feature/lstm-model | Medium | To Do
SA-106 | Model Integration | Integrate trained model with Flask backend | 5 | Anjali | feature/model-integration | High | To Do
SA-107 | Frontend UI | Design simple UI for text input and sentiment output display | 3 | Sneha | feature/frontend-ui | Medium | To Do
SA-108 | Prediction API Endpoint | Create Flask route for sentiment prediction | 3 | Pawan | feature/prediction-api | High | To Do
SA-109 | Testing & Validation | Unit testing and model accuracy validation | 5 | Rahul | feature/testing-validation | Medium | To Do
SA-110 | Deployment on Render | Configure and deploy application using Gunicorn on Render | 8 | Anjali | feature/deployment-render | High | To Do
SA-111 | Documentation | Prepare README and deployment documentation | 2 | Sneha | feature/documentation | Low | To Do